## Sheet1
Task	Time To Complete	Done	Actual Time To Finish
Search Internet For Sound Effects	30 Mins	Yes	2 mins
Implement Sound Effects	1 Hour	Yes	5 Mins
Implement Looping Background Music	2 Hour	Yes	10 Mins
Create a Sound Manager For Playing Sounds	2 Hours	Yes	1 Hour
Add Final Product Quality Sound Effects	3 Hours
Edit Background Music In Audacity to Remove Dubstep Parts	2 Hours

Create Enemy Sprites	30 Mins	Yes	5 Mins
Implement Basic Enemy	2 Hours	Yes	2 Hours
Include Enemy In Level Editor	1 Hour	Yes	5 Mins
Edit Enemy2's Up/Down Movement Glitch (To Do With Respawning)	20 Mins	Yes	20 Mins
Implement Animated Enemies	30 Mins	Yes	1 Hour, 30 Mins
Fix glitch with placing enemies where whole sprite sheet is placed	30 Mins	Yes	1 Hour

Create Three Backgrounds	30 Mins	Yes	30 Mins
Implement Tiled Background	3 Hours	Yes	1 Hour

Update User Input Class To Take Strings As Test	2 Hours	Yes	1 Hour
Update User Input Class To Test Key Releases	3 Hours
Update User Input Class To Return Key Currently Being Pressed	30 Mins	Yes	40 Mins
Allow the Player to be Controlled by the Mouse	2 Hours	Yes	1 Hour

Create A Level System	3 Hours	Yes	3 Hours

Implement Animated Sprites	2 Hours	Yes	2 Hours
Extend Animated Sprite Functionality	2 Hours

Create Rocket Smoke Particle Effect	2 Hours	Yes	3 Hours
Create Fire Particle Effect	1 Hour
Create Rain Particle Effects	1 Hour
Allow Particle Effects to be Placed in Level Editor	1 Hour

Make Window Resizeable (NOT USED ANYMORE)	2 Hours	Yes	20 Mins
Lock Window so it Can't be Resized	5 Mins	Yes	5 Mins

Create a Proper Main Menu	4 Hours
Add a How To Play Screen	20 Mins	Yes	40 Mins
Fix Menu so Level Editor works with it	30 Mins	Yes	30 Mins

Implement Basic Save-Load Feature (Autosave at Save At Checkpoints)	2 Hours
Add a Load Option on the Main Menu	2 Hours	Yes	1 Hour

Implement Couch Coop Mode	2 Hours

Clean Up The Text and Font Manager Coding!	2 Hours

Make Player Have Acceleration Instead of a Flat-Out Speed	3 Hours	Yes	2 Hours
Allow Player to Perform Diagonal Shots by moving up/down and shooting	30 Mins
Change Player Shooting So They Tap Space Instead of Hold it	20 Mins	Yes	10 Mins
Fully Implement Player's Animations	2 Hours	Yes	40 Mins
Make Mouse Controls Smoother and Less Clunky	1 Hour

Create a Final Boss	2 Hour	Yes	1 Hour
Give Boss Health	1 Hour	Yes	30 Mins
Make Boss Move Up and Down	1 Hour	Yes	20 Mins
Make Boss Shoot	1 Hour	Yes	45 Mins
Animate Boss	30 Mins

Make Final Boss do Diagonal Shots Based on Whether They're Going Up/Down	30 Mins

Add a Proper Pause Menu	2 Hours	Yes	1 Hour

Have a Thanks For Playing Screen	1 Hour	Yes	30 Mins